PROJECT ROADMAP

Banking Management System

A Python Desktop Application (Tkinter GUI + SQLite Database)

Academic / Semester Project — Brainware University

| Project Manager / Backend & Database Developer / Documentation Lead | Ramdas Hembram |
| --- | --- |
| Frontend/UI Developer / Testing & QA | Aditto Rudra |
| Duration | 10 Weeks |
| Technology Stack | Python, Tkinter, SQLite3 |

# 1. Project Overview

The Banking Management System is a desktop application that simulates core banking operations — customer account creation with an auto-generated account number, secure PIN-based login, cash deposit and withdrawal, fund transfer between accounts, transaction history logging, and an administrator panel for oversight and account management. The system is built using Python with a Tkinter graphical interface and an SQLite relational database for persistent storage.

This roadmap spans 10 weeks and is structured to balance workload evenly between the two team members while reflecting their assigned roles: Ramdas Hembram leads project management, backend logic, database design, and documentation; Aditto Rudra leads UI/UX design and implementation, along with testing and quality assurance.

## Objectives

- Deliver a fully functional, secure, and user-friendly banking desktop application.

- Demonstrate sound software engineering practice: requirements, design, modular development, testing, and documentation.

- Produce a polished, modern Tkinter interface that elevates the project beyond a typical academic CLI-style submission.

- Maintain balanced contribution and clear accountability between both team members.

# 2. Team Roles & Responsibilities

| Member | Primary Roles | Core Responsibilities |
| --- | --- | --- |
| Ramdas Hembram | Project Manager, Backend Developer, Database Developer, Documentation Lead | Requirement analysis, task scheduling, SQLite schema design, backend business logic (accounts, transactions, authentication), admin panel logic, SRS/report writing, coordination between modules. |
| Aditto Rudra | Frontend/UI Developer, Testing & Quality Assurance | Wireframing, Tkinter screen design, UI styling/theme, navigation flow, input validation on UI, integration testing, bug tracking, test-case design, user acceptance testing. |

# 3. Project Phases

The project is organized into seven phases mapped across a 10-week timeline:

- Phase 1: Initiation

- Phase 2: Planning & Requirement Analysis

- Phase 3: System & UI Design

- Phase 4: Development (Backend + Frontend, parallel tracks)

- Phase 5: Integration

- Phase 6: Testing & Quality Assurance

- Phase 7: Deployment, Documentation & Presentation

# 4. Week-by-Week Timeline & Milestones

| Week | Phase | Focus / Milestone | Owner(s) |
| --- | --- | --- | --- |
| Week 1 | Initiation | Project charter finalized; topic approval from faculty guide; roles confirmed; GitHub repo created | Both (Ramdas leads) |
| Week 2 | Planning | Requirement gathering; SRS document drafted; feature list & scope locked; DB entity list drafted | Ramdas (SRS), Aditto (feature UX input) |
| Week 3 | Design | ER diagram & SQLite schema finalized; wireframes for all screens; UI theme/style guide chosen | Ramdas (DB design), Aditto (wireframes/theme) |
| Week 4 | Development | Milestone: Database layer complete; login/signup screens built (static) | Ramdas (DB + auth logic), Aditto (UI screens) |
| Week 5 | Development | Account creation + auto account-number generation; Dashboard UI complete | Ramdas (backend), Aditto (frontend) |
| Week 6 | Development | Deposit/Withdraw modules; corresponding UI forms + validation | Ramdas (logic), Aditto (UI + validation) |
| Week 7 | Development | Milestone: Fund transfer module; transaction history module (backend + UI table view) | Ramdas (logic), Aditto (UI) |
| Week 8 | Integration | Admin panel (view/search/freeze accounts, view all transactions); full module integration | Ramdas (admin backend), Aditto (admin UI) |
| Week 9 | Testing & QA | Milestone: Unit + integration testing; bug fixing; UI polish and consistency pass | Aditto leads testing; Ramdas fixes backend bugs |
| Week 10 | Deployment & Docs | Milestone: Final build packaged; final report, user manual, PPT prepared; rehearsal & submission | Both (Ramdas: report, Aditto: manual/demo) |

# 5. Detailed Tasks per Phase

## Phase 1 — Initiation (Week 1)

| Task | Assigned To | Notes |
| --- | --- | --- |
| Define project title, scope, and objectives | Ramdas Hembram | Aligned with faculty guidelines |
| Get topic approved by project guide | Ramdas Hembram | Formal sign-off needed before Planning |
| Set up GitHub repository, folder structure, README | Ramdas Hembram | Shared with Aditto as collaborator |
| Set up local Python environment (venv, Tkinter, sqlite3 check) | Aditto Rudra | Ensures both machines are dev-ready |
| Create shared communication channel & task board | Both | See Tools section |

## Phase 2 — Planning & Requirement Analysis (Week 2)

| Task | Assigned To | Notes |
| --- | --- | --- |
| Gather functional & non-functional requirements | Ramdas Hembram | Interviews with guide, banking-app research |
| Draft Software Requirement Specification (SRS) | Ramdas Hembram | Deliverable of this phase |
| List required screens & user flows for UI | Aditto Rudra | Feeds directly into wireframing |
| Define feature list & prioritize (MoSCoW) | Both | Locks scope before design starts |
| Draft initial entity list for database (Users, Accounts, Transactions, Admin) | Ramdas Hembram | Input to ER diagram |

## Phase 3 — System & UI Design (Week 3)

| Task | Assigned To | Notes |
| --- | --- | --- |
| Design ER diagram (Accounts, Users, Transactions, Admin tables) | Ramdas Hembram | Depends on entity list (Phase 2) |
| Finalize SQLite schema (tables, keys, constraints) | Ramdas Hembram | Depends on ER diagram |
| Design account-number auto-generation logic (e.g., prefix + sequence) | Ramdas Hembram | Documented before coding starts |
| Create low-fidelity wireframes for all screens (Login, Signup, Dashboard, Deposit/Withdraw, Transfer, History, Admin) | Aditto Rudra | Depends on screen list (Phase 2) |
| Choose UI theme: color palette, fonts, custom Tkinter styling (ttk themes/icons) | Aditto Rudra | Key input for the "great UI" goal |
| Review & approve design jointly | Both | Gate before Development starts |

## Phase 4 — Development (Weeks 4–7, parallel tracks)

| Task | Assigned To | Notes |
| --- | --- | --- |
| Implement SQLite database creation script & connection handler | Ramdas Hembram | Foundation for all backend modules |
| Build authentication module (PIN hashing, login/signup logic) | Ramdas Hembram | Security-critical; uses hashing (e.g., hashlib) |
| Build account creation logic + auto account-number generator | Ramdas Hembram | Depends on DB schema |
| Build deposit / withdraw / balance-update logic with validation | Ramdas Hembram | Depends on account module |
| Build fund transfer logic (atomic debit/credit transaction) | Ramdas Hembram | Depends on deposit/withdraw logic |
| Build transaction history logging & retrieval queries | Ramdas Hembram | Runs alongside every money-movement function |
| Build admin backend (view users, freeze/unfreeze, view all transactions) | Ramdas Hembram | Depends on core modules being stable |
| Build Login & Signup screens in Tkinter (styled per theme) | Aditto Rudra | Depends on wireframes |
| Build Dashboard screen (balance display, navigation menu) | Aditto Rudra | Depends on login screen + backend session data |
| Build Deposit/Withdraw forms with input validation & confirmation dialogs | Aditto Rudra | Depends on backend function signatures |
| Build Fund Transfer screen (recipient lookup, amount entry, confirmation) | Aditto Rudra | Depends on transfer backend |
| Build Transaction History screen (scrollable table / Treeview widget) | Aditto Rudra | Depends on history backend |
| Build Admin Panel UI (account search, freeze toggle, reports view) | Aditto Rudra | Depends on admin backend |
| Apply consistent styling, icons, hover effects, error/success banners across all screens | Aditto Rudra | Ongoing — the "great UI" polish pass |

## Phase 5 — Integration (Week 8)

| Task | Assigned To | Notes |
| --- | --- | --- |
| Connect all UI screens to backend functions end-to-end | Both | Joint session recommended |
| Resolve data-flow issues between UI and database layer | Ramdas Hembram | Backend-side fixes |
| Verify navigation flow matches wireframes; fix layout breaks | Aditto Rudra | UI-side fixes |
| Freeze feature set for testing (no new features after this point) | Both | Gate before Testing phase |

## Phase 6 — Testing & Quality Assurance (Week 9)

| Task | Assigned To | Notes |
| --- | --- | --- |
| Write test cases covering all modules (login, transactions, transfer, admin) | Aditto Rudra | Deliverable: Test Case document |
| Execute functional & UI testing; log defects | Aditto Rudra | Uses bug tracker (see Tools) |
| Perform edge-case testing (negative amounts, insufficient balance, wrong PIN attempts) | Aditto Rudra | Security & robustness focus |
| Fix backend bugs identified during testing | Ramdas Hembram | Depends on defect log |
| Fix UI bugs and refine visual consistency | Aditto Rudra | Final polish pass |
| Regression test after fixes | Both | Confirms stability before packaging |

## Phase 7 — Deployment, Documentation & Presentation (Week 10)

| Task | Assigned To | Notes |
| --- | --- | --- |
| Package final application (requirements.txt, run instructions, .exe optional via PyInstaller) | Ramdas Hembram | Deliverable: deployable build |
| Write final project report (SRS, design, implementation, testing, conclusion) | Ramdas Hembram | Deliverable: Final Report |
| Prepare user manual / admin manual | Aditto Rudra | Deliverable: User Manual |
| Prepare presentation slides & live demo script | Both | Deliverable: PPT + demo |
| Rehearse demo, prepare Q&A for viva/faculty review | Both | Final readiness check |

# 6. Deliverables by Phase

| Phase | Deliverable(s) |
| --- | --- |
| Initiation | Approved project topic; GitHub repository |
| Planning | Software Requirement Specification (SRS) document |
| Design | ER diagram; SQLite schema document; wireframes; UI style guide |
| Development | Working modules: Auth, Accounts, Deposit/Withdraw, Transfer, History, Admin (backend + UI) |
| Integration | Fully connected working application (feature-complete build) |
| Testing & QA | Test case document; defect log; test summary report |
| Deployment & Docs | Final packaged application; final project report; user manual; presentation slides |

# 7. Key Task Dependencies

- SRS (Phase 2) must be approved before ER diagram and wireframes (Phase 3) begin.

- SQLite schema (Phase 3) must be finalized before any backend module coding (Phase 4) starts.

- Wireframes and UI theme (Phase 3) must be approved before Tkinter screen development (Phase 4) starts.

- Authentication module must be completed before Dashboard and session-dependent screens can be built.

- Deposit/Withdraw logic must exist before Fund Transfer logic can be implemented (transfer reuses debit/credit functions).

- Core modules (Accounts, Transactions) must be stable before the Admin Panel (which reads/manages them) is built.

- All modules must be integrated (Phase 5) before formal Testing (Phase 6) begins.

- Testing sign-off must occur before final packaging and documentation (Phase 7).

# 8. Risk Management

| Risk | Likelihood / Impact | Mitigation Strategy |
| --- | --- | --- |
| Scope creep — adding extra features mid-development (e.g., loans, interest calculators) delaying the core system | Medium / High | Lock feature scope at end of Planning phase (MoSCoW prioritization); treat extras as "nice-to-have" stretch goals only after core features are stable. |
| Data loss or corruption in SQLite (e.g., concurrent writes, incomplete transactions during transfer) | Medium / High | Use atomic transactions (BEGIN/COMMIT/ROLLBACK) for all money-movement operations; maintain regular backups of the .db file during development; test failure scenarios explicitly. |
| Uneven workload or schedule slippage due to exams/other commitments (common in academic projects) | High / Medium | Weekly check-in meetings with a shared task board; buffer built into Week 9–10; tasks broken into small, trackable units with clear owners per the table above. |
| UI not meeting the "great UI" expectation — looking like a default/plain Tkinter app | Medium / Medium | Dedicate explicit design time in Phase 3 (theme, wireframes); use ttk styled widgets, consistent color palette, icons, and Treeview for tables rather than default widgets; run a UI polish pass in Week 9. |
| Security gaps — PINs stored in plain text, weak login validation | Low / High | Hash PINs before storage (e.g., hashlib/sha256 with salt); enforce PIN format validation and limit failed login attempts; document security measures in the final report. |

# 9. Tools & Resources

| Purpose | Tool(s) |
| --- | --- |
| Version Control | Git & GitHub (shared repository, feature branches, pull requests) |
| Communication & Task Tracking | WhatsApp/Discord for daily communication; Trello or GitHub Projects (Kanban board) for task tracking |
| UI/UX Design & Wireframing | Figma or Canva for wireframes; Tkinter + ttk (styled widgets), ttkbootstrap or custom themes for the "great UI" look |
| Backend Development | Python 3.x, sqlite3 (standard library), hashlib (PIN hashing) |
| Database Management/Inspection | DB Browser for SQLite |
| Testing | Python unittest / pytest for backend logic; manual test-case checklist for UI/UX |
| Documentation | Microsoft Word / Google Docs for SRS and final report; draw.io or Lucidchart for ER diagrams |
| Presentation | Microsoft PowerPoint / Canva for slides |
| Packaging (optional) | PyInstaller to produce a standalone .exe for demonstration |

# 10. Workload Balance Summary

Both members carry a comparable load across the 10 weeks: Ramdas Hembram's effort is concentrated in backend/database logic and documentation, which are heavier in Weeks 2–8 but taper off during Weeks 9–10 (backend bug-fixing only). Aditto Rudra's effort is concentrated in UI development through Weeks 4–8, then intensifies in Weeks 9–10 as the lead for testing, QA, and the user manual. This creates a natural handoff where each member is at peak effort during complementary windows, keeping the overall pace balanced.

| Member | Weeks 1–3 (Foundation) | Weeks 4–8 (Build) | Weeks 9–10 (Finish) |
| --- | --- | --- | --- |
| Ramdas Hembram | High (SRS, schema, planning) | High (all backend modules, admin logic) | Medium (bug fixes, final report) |
| Aditto Rudra | Medium (wireframes, theme, env setup) | High (all UI screens, styling) | High (testing, QA, manual, demo) |

# 11. Achieving the "Great UI" Requirement

- A dedicated design step (Phase 3, Week 3) precedes any coding — wireframes and a color/typography style guide are agreed upon first.

- Use of ttk styled widgets and a custom theme (via ttkbootstrap or manual ttk.Style configuration) instead of raw default Tkinter widgets.

- Treeview widgets for transaction history and admin tables instead of plain text listings, giving a spreadsheet-like, professional feel.

- Consistent iconography, spacing, and color-coded feedback (e.g., green for success, red for errors) across all screens.

- A dedicated UI polish pass scheduled in Week 9 alongside testing, ensuring visual consistency is treated as a deliverable, not an afterthought.

Prepared for academic submission — Brainware University.